## TestCases
Test Suite/Scenario | TestCaseID - Name | Priority | Test Steps | Test Data | Expected Result | Actual Result | Pass/Fail/Blocked | BUG number
Interface Login | 1 - Verify username and password correct+login button | p1 | 1. go to link 2. go to the login page 3. input correct username 4. input correct password 5. press login button | username:Raluca01 password:2356 | redirect to homepage | redirect to homepage | PASS
| 2 - Verify username correct and incorrect password+login button | p1 | 1. go to link 2. go to the login page 3. input correct username 4. input incorrect password 5. press login button | username:Raluca01 password:4567 | error:username and password do not match any user in this service | error:username and password do not match any user in this service | PASS
| 3 -verify username correct and password field empty+login button | p1 | 1. go to link 2. go to the login page 3. input correct username 4. input field empty password 5. press login button | username:Raluca01 password: | error:password is required | error:password is required | PASS
Product List interface | 4-Verify Menu button | p2 | 1. go to link 2. go to the main page 3. press menu button | all items : home page about :product redirection logout reset app state | all the buttons are displayed | all the buttons are displayed | PASS
| 5- Verify all items button | p2 | 1. go to link 2. go to the main page 3. press menu button 4. press All items button | menu button all items button | when clicking on the all items button, the user should be redirected to home button | the user is not redirected to the home button | FAIL | BUG#1
| 6-About button | p2 | 1. go to link 2. go to the main page 3. press menu button 4. press About button | menu button about button | when clicking on the about button, the user should be redirected products page | when clicking on the about button, the user should be redirected products page | PASS
| 7- Logout button | p2 | 1. go to link 2. go to the main page 3. press menu button 4. press Logout button | menu button logout button | when clicking on the Logout button, the user should be logged out | when clicking on the Logout button, the user should be logged out | PASS
| 8- Product list | p2 | 1. go to link 2. go to the login page 3. go to main page | login page main page | we should see a list of six products | we should see a list of six products | PASS
| 9- Sort button (A/Z) | p2 | 1. go to link 2. go to the main page 3. press sort button (A/Z) | sort button | products are sorted correctly (A/Z) | products are sorted correctly (A/Z) | PASS
| 10- Sort button (Z/A) | p2 | 1. go to link 2. go to the main page 3. press sort button (Z/A) | sort button | products are sorted correctly (Z/A) | products are sorted correctly (Z/A) | PASS
| 11 - Sort button by price (low to high) | p2 | 1. go to link 2. go to the main page 3. press sort button by price (low to high) | sort button | products are sorted correctly by price (low to high) | products are sorted correctly by price (low to high) | PASS
| 12 - Sort button by price (high to low) | p2 | 1. go to link 2. go to the main page 3. press sort button by price (high to low) | sort button | products are sorted correctly by price (high to low) | products are sorted correctly by price (high to low) | PASS
| 13 - Add to cart button for one product | p1 | 1. go to link 2. go to the main page 3. add to cart one product | add to cart button one product | the product is added to the cart with success | the product is added to the cart with success | PASS
| 14 - Add to cart button is changed into remove | p2 | 1. go to link 2. go to the main page 3. add to cart one product | add to cart button one product remove button | Add to cart button should be changed into remove | Add to cart button it changes into remove | PASS
| 14 - Add to cart button for six products | p1 | 1. go to link 2. go to the main page 3. add to cart six products | add to cart button six products | the products are added to the cart with success | the products are added to the cart with success | PASS
Single product page interface | 15 - Check product details | p2 | 1. go to link 2. go to the main page 3. select a product | product page | the product contains all the details required | the product contains all the details required | PASS
| 16 - Back to products button | p1 | 1. go to link 2. go to the main page 3. select a product 4. click on back to products button | product page back to products button | the user is redirected to the all products page when clicking on the back to products button | the user is redirected to the all products page when clicking on the back to products button | PASS
Shopping cart interface | 17 - Remove button | p1 | 1. go to link 2. go to the main page 3. go to shopping cart | shopping cart remove product button | product should be removed from the cart | product is removed from the cart | PASS
| 18 - Continue shopping button | p1 | 1. go to link 2. go to the main page 3. go to shopping cart | shopping cart continue shopping button | when clicking on the continue shopping button, the user should be redirected to the main page | when clicking on the continue shopping button, the user should be redirected to the main page | PASS
| 19 - Product details in shopping cart | p1 | 1. go to link 2. go to the main page 3. go to shopping cart | shopping cart product details | all product details should be correct in the shopping cart (price, quantity) | all product details should be correct in the shopping cart (price, quantity) | PASS
Checkout Interface | 20 - Checkout with correct data for customer | p1 | 1. go to link 2. go to the main page 3. go to shopping cart 4. go to checkout | shopping cart checkout page customer data | user does the checkout with success | user does the checkout with success | PASS
| 21 - Checkout with first name empty ,last name completed,zip/postal code completed | p1 | 1. go to link 2. go to the main page 3. go to shopping cart 4. go to checkout | shopping cart checkout page first name empty last name completed zip/postal code completed | "First name required" error should be displayed | Error:First name is required | PASS
| 22 - Checkout with first name completed ,last name empty, zip/postal code completed | p1 | 1. go to link 2. go to the main page 3. go to shopping cart 4. go to checkout | shopping cart checkout page first name completed last name empty zip/postal code completed | "Last name required" error should be displayed | Error:Last name is required | PASS
| 23 - Checkout with first name completed ,last name completed,zip/postal code empty | p1 | 1. go to link 2. go to the main page 3. go to shopping cart 4. go to checkout | shopping cart checkout page first name completed last name completed zip/postal code empty | "zip/postal code required" error should be displayed | Error:Postal code is required | PASS
| 24 - Continue button | p1 | 1. go to link 2. go to the main page 3. go to shopping cart 4. go to checkout 5. click on continue button | shopping cart checkout page continue button | user should be redirected to checkout overview page | user is redirected to checkout overview page | PASS
| 25 - Cancel button | p1 | 1. go to link 2. go to the main page 3. go to shopping cart 4. go to checkout 5. click on cancel button | shopping cart checkout page cancel button | user should be redirected to products list page | user is redirected to products list page | PASS
| 26 - Finish button | p1 | 1. go to link 2. go to the main page 3. go to shopping cart 4. go to checkout 5. click on finish button | shopping cart checkout page finish button | user should be redirected to place order confirmation page | user is redirected to place order confirmation page | PASS
| 28 - Back to home button | p1 | 1. go to link 2. go to the main page 3. go to shopping cart 4. go to checkout 5. click on back to home button | shopping cart checkout page back to home button | user should be redirected home page | user is redirected to the home page | PASS
| 29- Add products to the cart-logout | p2 | 1. go to link 2. go to the main page 3. add to cart products 4.click logout | add to cart products click logout | when I re-enter the account, the products should remain saved | when I re-enter the account, the products should remain saved | PASS
| 30-Source code should not appear on the site | p1 | 1. go to link 2. go to the main page 3.go to products page 4.look for source code in the page | products page | all the text is correctly written | carry.allTheThings() and test.allTheThings() are displayed on the products page | FAIL | BUG#2

## Results
Total tests | Nb of Pass test | Nb of Failed test | Nb. Of Blocked tests | Total test covered | Blocked Tests% | Failed test% | Pass test % | Total test covered
5 | 4 | 1 | 0 | 5 | 0 | 20 | 80 | 100