## TestCases
Test Suite/Scenario | TestCaseID - Name | Priority | Test Steps | Test Data | Expected Result | Actual Result | Pass/Fail/Blocked | BUG number
Interface Login | 1 - Verify username and password correct+login button | p1 | 1. go to link 2. go to the login page 3. input correct username 4. input correct password 5. press login button | username:problem_user password:secret_sauce | redirect to homepage | redirect to homepage | PASS
| 2 - Verify username correct and incorrect password+login button | p1 | 1. go to link 2. go to the login page 3. input correct username 4. input incorrect password 5. press login button | username:problem_user password:2345 | error:username and password do not match any user in this service | error:username and password do not match any user in this service | PASS
| 3 -verify username correct and password field empty+login button | p1 | 1. go to link 2. go to the login page 3. input correct username 4. input field empty password 5. press login button | username:Raluca01 password: | error:password is required | error:password is required | PASS
Product List interface | 4-Verify Menu button | p2 | 1. go to link 2. go to the main page 3. press menu button | all items : home page about :product redirection logout reset app state | all the buttons are displayed | all the buttons are displayed | PASS
| 5- Verify all items button | p2 | 1. go to link 2. go to the main page 3. press menu button 4. press All items button | menu button all items button | when clicking on the all items button, the user should be redirected to home button | the user is not redirected to the home button | FAIL | BUG#4
| 6-About button | p2 | 1. go to link 2. go to the main page 3. press menu button 4. press About button | menu button about button | when clicking on the about button, the user should be redirected products page | when clicking on the about button, the user is not redirected to the products page | FAIL | BUG#5
| 7- Logout button | p2 | 1. go to link 2. go to the main page 3. press menu button 4. press Logout button | menu button logout button | when clicking on the Logout button, the user should be logged out | when clicking on the Logout button, the user should be logged out | PASS
| 8- Product list | p2 | 1. go to link 2. go to the login page 3. go to main page | login page main page | we should see a list of six products | we should see a list of six products | PASS
| 9- Sort button (A/Z) | p2 | 1. go to link 2. go to the main page 3. press sort button (A/Z) | sort button | products are sorted correctly (A/Z) | products are sorted correctly (A/Z) | PASS
| 10- Sort button (Z/A) | p2 | 1. go to link 2. go to the main page 3. press sort button (Z/A) | sort button | products are sorted correctly (Z/A) | products are not sorted correctly (Z/A) | FAIL | BUG#6
| 11 - Sort button by price (low to high) | p2 | 1. go to link 2. go to the main page 3. press sort button by price (low to high) | sort button | products are sorted correctly by price (low to high) | products are not sorted correctly by price (low to high) | FAIL | BUG#7
| 12 - Sort button by price (high to low) | p2 | 1. go to link 2. go to the main page 3. press sort button by price (high to low) | sort button | products are sorted correctly by price (high to low) | products are not sorted correctly by price (high to low) | FAIL | BUG#8
| 13 - Add to cart button for one product | p1 | 1. go to link 2. go to the main page 3. add to cart one product | add to cart button one product | the product is added to the cart with success | the product is added to the cart with success | PASS
| 14 - Add to cart button is changed into remove | p2 | 1. go to link 2. go to the main page 3. add to cart one product | add to cart button one product remove button | Add to cart button should be changed into remove | Add to cart button is changed into remove | PASS
| 14 - Add to cart button for six products | p1 | 1. go to link 2. go to the main page 3. add to cart six products | add to cart button six products | the products are added to the cart with success | the products are not added to the cart with success | FAIL | BUG#9
Single product page interface | 15 - Check product details | p2 | 1. go to link 2. go to the main page 3. select a product | product page | the product contains all the details required | the product are not contains all the details required | FAIL | BUG#10
| 16 - Back to products button | p1 | 1. go to link 2. go to the main page 3. select a product 4. click on back to products button | product page back to products button | the user is redirected to the all products page when clicking on the back to products button | the user is redirected to the all products page when clicking on the back to products button | PASS
Shopping cart interface | 17 - Remove button | p1 | 1. go to link 2. go to the main page 3. go to shopping cart | shopping cart remove product button | product should be removed from the cart | product is removed from the cart | PASS
| 18 - Continue shopping button | p1 | 1. go to link 2. go to the main page 3. go to shopping cart | shopping cart continue shopping button | when clicking on the continue shopping button, the user should be redirected to the main page | when clicking on the continue shopping button, the user should be redirected to the main page | PASS
| 19 - Product details in shopping cart | p1 | 1. go to link 2. go to the main page 3. go to shopping cart | shopping cart product details | all product details should be correct in the shopping cart (price, quantity) | all product details should be correct in the shopping cart (price, quantity) | PASS
Checkout Interface | 20 - Checkout with correct data for customer | p1 | 1. go to link 2. go to the main page 3. go to shopping cart 4. go to checkout | shopping cart checkout page customer data | user does the checkout with success | Last name is displayed instead of first name and “last name is required” error is displayed in the page | FAIL | BUG#11
| 21 - Checkout with first name empty ,last name completed,zip/postal code completed | p1 | 1. go to link 2. go to the main page 3. go to shopping cart 4. go to checkout | shopping cart checkout page first name empty last name completed zip/postal code completed | "First name required" error should be displayed | “last name is required” error is displayed in the page instead of “first name is required error” | FAIL | BUG#12
| 22 - Checkout with first name completed ,last name empty, zip/postal code completed | p1 | 1. go to link 2. go to the main page 3. go to shopping cart 4. go to checkout | shopping cart checkout page first name completed last name empty zip/postal code completed | "Last name required" error should be displayed | "Last name required" error is displayed | PASS
| 23 - Checkout with first name completed ,last name completed,zip/postal code empty | p1 | 1. go to link 2. go to the main page 3. go to shopping cart 4. go to checkout | shopping cart checkout page first name completed last name completed zip/postal code empty | "zip/postal code required" error should be displayed | “last name is required” error is displayed in the page instead of “zip/postal code is required error” | FAIL | BUG#13
| 24 - Continue button | p1 | 1. go to link 2. go to the main page 3. go to shopping cart 4. go to checkout 5. click on continue button | shopping cart checkout page continue button | user should be redirected to checkout overview page | “last name is required” error is displayed in the page instead of overview page | FAIL | BUG#14
| 25 - Cancel button | p1 | 1. go to link 2. go to the main page 3. go to shopping cart 4. go to checkout 5. click on cancel button | shopping cart checkout page cancel button | user should be redirected to checkout page | user is redirected to checkout page | PASS
| 26 - Finish button | p1 | 1. go to link 2. go to the main page 3. go to shopping cart 4. go to checkout 5. click on continue button 6. go to checkout overview | shopping cart checkout overview page continue button | user should be redirected to place order confirmation page | continue button fails to open checkout overview page | FAIL | BUG#15
| 28 - Back to home button | p1 | 1. go to link 2. go to the main page 3. go to shopping cart 4. go to checkout 5. click on continue button 6. go to checkout overview 7. click on back to home button | shopping cart checkout page back to home button checkout overview page | user should be redirected home page | continue button fails to open checkout overview page | BLOCKED | BUG#15
| 29- Add products to the cart-logout | p2 | 1. go to link 2. go to the main page 3. add to cart products 4.click logout | add to cart products click logout | when I re-enter the account, the products should remain saved | when I re-enter the account, the products remain saved | PASS
| 30-Source code should not appear on the site | p1 | 1. go to link 2. go to the main page 3.go to products page 4.look for source code in the page | products page | all the text is correctly written | carry.allTheThings() and test.allTheThings() are displayed on the products page | FAIL | BUG#16

## Results
Total tests | Nb of Pass test | Nb of Failed test | Nb. Of Blocked tests | Total test covered | Blocked Tests% | Failed test% | Pass test % | Total test covered
5 | 4 | 1 | 0 | 5 | 0 | 20 | 80 | 100